VAJZ

Assessment & Placement Preparation Platform

Implementation Plan

Phased Delivery Roadmap & Team Plan

Document type: Implementation Plan

Version 1.0  |  August 9, 2026

Status: Draft for Review

# 1. Delivery Approach

Three phases over roughly 12 weeks: Phase 1 (MVP) gets a T&P coordinator from question authoring to a published, group-targeted assessment and a candidate through login → take → submit. Phase 2 adds proctoring, reporting depth, and bulk operations. Phase 3 hardens scale, adds analytics, and applies the comic-book design system end-to-end.

# 2. Phased Roadmap

## Phase 1 — MVP (Weeks 1–5)

| Workstream | Deliverables |
| --- | --- |
| Foundation | Auth (JWT/RBAC), User Management (Roles, Users, Groups CRUD), base design-token library |
| Question Bank | Create/edit MCQ, Coding, Fill-Up questions; question list with filters |
| Assessment Builder | Create assessment with sections, marks, negative marking |
| Administration | Create administration (duration, start/end), basic access settings (show score/answers) |
| Publish | Publish & Invite by selecting Group(s); email notification on publish |
| Candidate Portal | Login, My Assessments list, Take Assessment (MCQ + Fill-Up), timer, submit |

## Phase 2 — Depth & Trust (Weeks 6–9)

| Workstream | Deliverables |
| --- | --- |
| Coding questions | Code editor, language selection, sandboxed execution, test-case grading |
| Proctoring | Webcam capture, tab-switch tracking & limits, IP restriction |
| Assessment config | Randomize questions/grading, retake count, restrict manual submit |
| Bulk operations | Bulk question upload (CSV/Excel), ad-hoc email invites/CSV alongside group publish |
| Reporting | Per-administration candidate report, individual detail view, CSV export |

## Phase 3 — Scale, Analytics & Polish (Weeks 10–12)

| Workstream | Deliverables |
| --- | --- |
| Design system rollout | Full comic-book visual system applied across Admin + Candidate surfaces, accessibility pass |
| Performance & scale | Load test to 2,000 concurrent candidates; autoscale API + code-execution pool |
| Analytics | Dashboard charts (hire-by/last-7-days style widgets), cohort/group comparisons |
| Hardening | Security review, audit logging, backup/DR runbook, staging → prod rollout |

# 3. Milestone Timeline

| Week | Milestone |
| --- | --- |
| 1–2 | Foundations: auth, RBAC, Groups/Users, design tokens ready |
| 3–4 | Question Bank + Assessment Builder complete; internal demo |
| 5 | MVP complete: Administration scheduling, Publish-by-Group, Candidate take-test flow end-to-end |
| 6–7 | Coding questions + sandboxed execution live; Proctoring v1 |
| 8–9 | Bulk upload, ad-hoc invites, full Reporting + CSV export |
| 10 | Design system rollout across both apps |
| 11 | Load testing, security review, analytics dashboard |
| 12 | UAT, bug bash, production rollout |

# 4. Team & Roles

| Role | Responsibility |
| --- | --- |
| Product Owner | Owns PRD, prioritization, stakeholder sign-off |
| Tech Lead / Architect | Owns TRD, architecture decisions, code review standards |
| Frontend Engineers (2) | Admin Console + Candidate Portal, design-system implementation |
| Backend Engineers (2) | API services, data model, code-execution sandbox integration |
| QA Engineer | Test plans, automation for scoring/timer/proctoring edge cases |
| UI/UX Designer | Comic-book design system, screen mockups, accessibility pass |
| DevOps | CI/CD, autoscaling, monitoring, backups |

# 5. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Concurrent test-start spikes overwhelm code-execution sandbox | Queue-based execution with autoscaled worker pool; load test before each major administration |
| Client clock drift causes unfair auto-submit | Server-side authoritative timer (Redis), client only displays countdown |
| Wrong Group selected on publish sends test to the wrong candidates | Live candidate-count preview + confirmation step before Publish & Invite; audit log of publish actions |
| Proctoring false positives frustrate candidates | Configurable thresholds; admin review step before flags affect scoring |
| Bulk question upload introduces malformed data | Strict template validation with row-level error reporting before import commits |

# 6. Testing & QA Plan

- Unit + integration tests for scoring logic (marks, negative marking, randomization).

- End-to-end tests covering: create question → build assessment → schedule → publish to group → candidate login → take → submit → report.

- Timer/auto-submit tests under simulated network latency and page-refresh mid-test.

- Proctoring event tests (tab-switch counting, snapshot capture, limit enforcement).

- Load testing for concurrent test-start and code-execution throughput.

- Accessibility audit (contrast, keyboard nav, screen-reader labels) against the bold comic-book palette.

# 7. Launch Checklist

- Security review sign-off (auth, RBAC, data encryption).

- Backup & disaster-recovery runbook validated.

- Monitoring/alerting live for API error rate, execution-queue depth, and email-delivery failures.

- UAT sign-off from T&P coordinator persona and a candidate pilot group.

- Rollback plan documented for the first live administration.